## Defects
Defect Analysis (3/1/2018 - 8/31/2018)
# | Quantity | Date | Defect Description | Root Cause | Corrective Action | Corrective Action Implementation Date | Has Defect Recurred (Y/N?)
1 | 4 | 2018-03-17 | Burrs on Housing | Worn Tooling | Implement preventive maintenance program on machining tools | 2018-03-31 | N
2 | 6 | 2018-05-01 | Missing Conformal Coating | Automated coating angle of application makes it difficult to coat component due to close proximity to another component, which blocks part of the coating application. | Coating this component manually during touch-up operation. Highlight this area in the work instructions. | 2018-05-08 | N
|  | 2018-05-01 |  | Component design does not allow the leads of the component to be coated because the component body is mounted flush to the board. | Change component design to allow leads to be exposed and coating to be applied. | 2018-07-27 | N
3 | 2 | 2018-03-29 | Image quality failure | Lens was found to have primer residue on surface. Primer is not easily identified because it has a clear color. | Change primer to a material that has a pink hue in order to make it more visible. | 2018-04-23 | N
4 | 1 | 2018-06-05 | Miswire | Operator error. Did not solder green wire to correct solder joint. | Review defect with operator and verify that work insturctions are sufficient regarding soldering requirements. | 2018-06-06 | N
5 | 8 | 2018-05-24 | Interference Fit | Subassembly could not be installed at hext higher assembly because the flex cable istalled was not formed correctly. The flex cable assembly is not kept in the forming tool after the curing cycle. This results in the flex cable not keeping its form. | Change the process to keep for flex assembly in the forming tool for 24 hours after the cure cycle. | 2018-06-03 | N
6 | 14 | 2018-03-02 | Configuration Error | The hardware configuration delivered by the supplier did not match the configuration (revision level) required on the purchase order. | Implemented electronic configuration control system at supplier that will automatically compare PO revision against hardware revision entered by production control when the hardware is issued to the production floor. | 2018-05-28 | N

## Defect_Timeline_Chart
Sum of Quantity | Column Labels
Row Labels | 2018-03-02 | 2018-05-24 | 2018-05-01 | 2018-03-17 | 2018-03-29 | 2018-06-05 | Grand Total
Configuration Error | 14 | [5 empty] | 14
Interference Fit |  | 8 |  |  |  |  | 8
Missing Conformal Coating |  |  | 6 |  |  |  | 6
Burrs on Housing |  |  |  | 4 |  |  | 4
Image quality failure |  |  |  |  | 2 |  | 2
Miswire | [5 empty] | 1 | 1
Grand Total | 14 | 8 | 6 | 4 | 2 | 1 | 35

## Pareto_Analysis
Failure Mode | 2018-03-02 | 2018-05-24 | 2018-05-01 | 2018-03-17 | 2018-03-29 | 2018-06-05 | Defects | Cumulative Value | Cumulative %
Configuration Error | 14 | [5 empty] | 14 | 14 | 40%
Interference Fit |  | 8 |  |  |  |  | 8 | 22 | 62.86%
Missing Conformal Coating |  |  | 6 |  |  |  | 6 | 28 | 80%
Burrs on Housing |  |  |  | 4 |  |  | 4 | 32 | 91.43%
Image quality failure |  |  |  |  | 2 |  | 2 | 34 | 97.14%
Miswire | [5 empty] | 1 | 1 | 35 | 100%
Grand Total | 14 | 8 | 6 | 4 | 2 | 1 | 35